## Functional areas
Functional/Non-functional area | Comments
Basic behavior | Going to background, sleeping, installation, start, navigation between screens, etc
Integration with Google | Installation from Store, Google Game suggestion popup behavior
Integration with Firebase | Out of scope for now (low priority)
Integration with the advertising service | Out of scope for now (low priority)
Localization | Texts, applying locale
Graphics (option 1) | All images, icons, splach screen etc (for all levels and screens)
Graphics (option 2) | All images, icons, splach screen etc (for all levels and screens)
Home screen | Functional part - work of the buttons, etc
Settings | Functional part - work of the buttons, etc
Sounds | All sounds and their setting
Game process | General logic of the game Switching between levels Unlocking levels Etc
Level 1 | Logic of particular level: Start level Leave level User wins User fails Tutorial Check 1 star adding Check 2 star adding Check 3 star adding Check level screen Etc
Level 2 | The same (except tutorial)
Level 3 | The same (except tutorial)
Level 4 | The same (except tutorial)
Level 5 | The same (except tutorial)
Level 6 | The same (except tutorial)
Level 7 | The same (except tutorial)
Level 8 | The same (except tutorial)
Level 9 | The same (except tutorial)
Level 10 | The same (except tutorial)
Level 11 | The same (except tutorial)
Level 12 | The same (except tutorial)
Level 13 | The same (except tutorial)
Level 14 | The same (except tutorial)
Level 15 | The same (except tutorial)
Level 16 | The same (except tutorial)
Level 17 | The same (except tutorial)
Level 18 | The same (except tutorial)
Level 19 | The same (except tutorial)
Level 20 | The same (except tutorial)
Level 21 | The same (except tutorial)
Level 22 | The same (except tutorial)
Level 23 | The same (except tutorial)
Level 24 | The same (except tutorial)
Survival mode | The same (except tutorial) + Score
Compatibility with non-Google devices | Low priority
Compatibility with different devices | Short regression on different devices. Will be done after we complete testing
User manual

## Sound
What to test | Expected result | Result |  | Comments
|  | Engineer | Reviewer
Localisation: home screen
Music at home screen | Music is playing constantly without pauses during 5 minutes | PASSED
The possibility to turn down the sound by pressing the volume control button at the device | The sound is turned down | PASSED
The possibility to turn off the sound by pressing the volume control button at the device | The sound is turned off | PASSED
The possibility to make the sound louder by pressing the volume control button at the device | The sound became louder | PASSED
The possibility to turn on the sound by pressing the volume control button at the device | The sound is turned on | PASSED
The presence of music after pressing the button "Tutorial" | The music continues to play | PASSED
The presence of music after pressing the button "Settings" | The music continues to play | PASSED
Localisation: settings
The possibility to turn down the sound by pressing on the slider in the "Settings" | The sound is turned down | PASSED
The possibility to turn off the sound by pressing on the slider in the "Settings" | The sound is turned off | PASSED
The possibility to make the sound louder by pressing on the slider in the "Settings" | The sound became louder | PASSED
The possibility to turn on the sound by pressing on the slider in the "Settings" | The sound is turned on | PASSED
Localisation: levels
The little man makes a sound when the player clicks on him | The sound is played | PASSED
The sound is not played when the player clicks on the empty cell | The sound is not played | PASSED
Little men make a sound when the player builds a line of three identical characters in a row | The sound is played | FAILED |  | Bug #4847: Little men do not make a sound when the player builds a line of three identical characters in a row
Little men make o sound when the player builds a line of five or more identical characters in a row | The sound is played | PASSED
The sound is played when the player chops down a tree with a hatchet | The sound is played | PASSED
The sound is played when the player presses the button "Help" | The sound is played | PASSED
The sound stops playing when little men have run away from the playing field | The sound stops playing | FAILED |  | Bug #4834 The sound continues to play when little men have run away from the playing field
The sound is played when the player collects the hatchet from the playing field | The sound is played | PASSED
Localisation: pause menu
The possibility to turn down the sound by pressing the volume control button at the device | The sound is turned down | PASSED
The possibility to turn off the sound by pressing the volume control button at the device | The sound is turned off | PASSED
The possibility to make the sound louder by pressing the volume control button at the device | The sound became louder | PASSED
The possibility to turn on the sound by pressing the volume control button at the device | The sound is turned on | PASSED
The possibility to turn down the sound by pressing on the slider in the "Pause" menu | The sound is turned down | PASSED
The possibility to turn off the sound by pressing on the slider in the "Pause" menu | The sound is turned off | PASSED
The possibility to make the sound louder by pressing on the slider in the "Pause" menu | The sound became louder | PASSED
The possibility to turn on the sound by pressing on the slider in the "Pause" menu | The sound is turned on | PASSED
The sound is played when the player wins the game | The sound is played | PASSED
The sound is played when the player loses the game | The sound is played | PASSED
Other
The work of sounds when the player uses headphones | Sound are played correctly | SKIPPED
The work of sounds at full volume | Sound are played correctly | PASSED
The work of sounds in different languages | Sound are played correctly | SKIPPED
The work of sound during the incoming call | The sound is turned off | SKIPPED
The work of sound during the incoming message | The sound is turned off | SKIPPED